## Slide 1: Construction Schedule Impact to Campus
Laura Stevenson Dumas
VP, Chief of Staff
April 10, 2024

## Slide 2: Facilities Offline
Flagler Room (through fall 2025)
Solarium (through January 2025)
Rotunda and Dhall (May - August
Pool (May – August)
Markland Parking Lot (June/July??)

## Slide 3: General Schedule
May 6 – 10
  Move out Ponce West furniture
  Rotunda Abatement Prep
  Scaffolding in Courtyard
May 13 through August
  Rotunda Abatement
    Limited access to admin wing mid-June
  Ponce West Abatement
  Ponce West first floor “surgical” demo
May 28 – August
  Chiller Underground Piping

## Slide 4: Ponce Schedule

## Slide 5: Underground Piping
Approx. 2 Weeks Per Run
Kenan
Ponce
Lewis
“Home Run”

## Slide 6: Third Floor Rotunda, “Birdcage”
Grand Opening
April 11!
10 a.m. – 11:30 a.m.